{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":10,"n_cols":11,"rows_kept":10,"cut":false,"hidden":false,"merged":[]}
["平台","项目模块","功能名称","计划开始时间","计划结束时间","实际开始时间","实际结束时间","项目进度百分比","优先级","负责人","备注"]
["App","基本功能","油机多媒体互动-限车牌自动识别","2019-03-13","2019-03-15","2019-03-13","2019-03-15",1,null,"谭家威"]
["App","基本功能","人脸识别-无感支付","2019-03-24","2019-03-26","2019-03-24",null,0.1,"高","谭家威","正在使用百度程序代码测试中"]
["App","基本功能","上传油枪状态等信息数据","2019-03-27","2019-03-28",null,null,0,"高","谭家威","接口文件已发送吴工，等待吴工支持"]
["App","基本功能","流媒体播放","2019-03-29","2019-03-30",null,null,0,"高","谭家威","初步使用nodeMedia实现流媒体播放功能（RTMP协议）"]
["App","基本功能","可视对讲","2019-04-01","2019-04-02",null,null,0,"高","谭家威","初步使用nodeMedia实现流媒体播放功能（RTMP协议）"]
["C++","基础功能","油气状态数据接口（重新用c++实现）","2019-03-25","2019-03-26","2019-03-25",null,0.25,"高","陈硕","接口调试过，但是之前使用nodejs实现，服务方数据接收没问题"]
["C++","基础功能","油罐压力数据接口（重新用c++实现）","2019-03-27","2019-03-27",null,null,0,"高","陈硕"]
["C++","基础功能","油气回收接口调试","2019-03-28","2019-03-29",null,null,0,"高","陈硕"]
["java","基础功能","防作弊系统数据上传到中石化第三方","2019-03-25","2019-03-31",null,null,0,"高","周福生","具体接口数量和具体形式还需中石化确定负责人后继续推进，周一催促中石化"]